## Project Charter & Team
BISY2004 PROJECT MANAGEMENT — ASSESSMENT 2 ARTEFACT
Project OmniPortal: University Student Portal Consolidation
Selected Scenario | Scenario C: University Student Portal Consolidation
Sponsoring Institution | Apex Metropolitan University (28,000 active students, 3,200 staff)
Business Problem / Need | Students navigate 4 disjointed legacy platforms (Blackboard LMS, Ellucian Banner SIS, TouchNet Fees, and Zendesk Support). Fragmented logins cause a 42% helpdesk enquiry load during enrolment, 18% record desynchronization, and high annual multi-vendor licensing costs ($185,000/yr).
Project Purpose | Deliver a centralized, cloud-hosted responsive web and mobile portal ('OmniPortal') integrating single sign-on (SSO), unified student records, course enrolment, timetable management, and automated tuition payment processing.
Key Objectives | 1. Complete consolidation within 24 weeks (120 working days) prior to Semester 1 enrolment. 2. Restrict total capital and operational expenditure to the approved $450,000 budget cap. 3. Achieve zero data loss during the migration of 28,000 student records. 4. Deliver 99.95% system uptime and sub-2.0s page load under a 12,000 concurrent user load.
Development Lifecycle | Hybrid Agile-Waterfall: Predictive Waterfall for Initial Architecture, Data Privacy Governance, Infrastructure Provisioning, and Final Deployment; 2-Week Agile Sprints for UX/UI wireframing, feature development, and API integration.
Approved Budget Cap | $450,000 AUD (Capex + Opex incl. 10% Contingency Reserve & 5% Management Reserve)
Project Baseline Window | Baseline Start: 02 February 2026 ¦ Baseline Finish: 17 July 2026 (24 Calendar Weeks)
GROUP MEMBERS & PROJECT ROLE RESPONSIBILITY MATRIX
Student Name | Student ID | Assigned Project Role | Assessment Responsibility | Maintained Artefacts
Tanvir Ahmed | 238983 | Project Lead & Systems Architect | Section 1 (Overview, Charter, Scope, WBS) & Section 2 (Schedule, Cost, Critical Path) | WBS (draw.io), ProjectLibre Schedule (.pod), Critical Path Analysis, Baseline Cost Model
Momen Ahmed | 242048 | Risk, Finance & Governance Lead | Section 3 (Risk Register, Heat Map, Stakeholder Analysis, Communication Plan) | Risk Register & 5x5 Heat Map, Stakeholder Matrix, Power-Interest Grid, Communication Plan
MD Rejvi Jaman Mafti | 241964 | Quality, Delivery & Tracking Lead | Section 4 (Quality, Change, RACI), Section 5 (Trello, Dashboard), Section 6 (Integration) | Quality Metrics, Change Log (CR-01), RACI Matrix, Trello Board, Status & EVM Dashboard

## WBS & Schedule Data
WORK BREAKDOWN STRUCTURE (WBS) & PROJECTLIBRE SCHEDULE DATA
Exact Task Breakdown, Predecessors, Durations, Resources, and Critical Path Tagging
Task ID | WBS Code | Task Name | Duration (Days) | Predecessors | Assigned Resources | Cost ($) | Critical Path?
1 | 1.0 | PROJECT INITIATION & GOVERNANCE | 15 |  | PM, Architect | 16500 | Yes
2 | 1.1 | Project Charter & Stakeholder Approval | 5 |  | PM, Sponsor | 4500 | Yes
3 | 1.2 | Project Management Plan & Risk Framework | 5 | 2 | PM | 3800 | Yes
4 | 1.3 | Initial Kickoff & Governance Committee | 5 | 3 | PM, All Leads | 8200 | Yes
5 | 1.4 | MILESTONE 1: Project Charter Signed Off | 0 | 4 | PM, Sponsor | 0 | Yes
6 | 2.0 | REQUIREMENTS & ARCHITECTURE | 20 |  | Architect, BA, Security | 31200 | Yes
7 | 2.1 | Stakeholder Requirements Gathering | 8 | 5 | BA, UX Lead | 9600 | Yes
8 | 2.2 | Data Privacy & Compliance Review (GDPR/APP) | 6 | 7 | Security Officer, BA | 6400 | No
9 | 2.3 | Technical Architecture & Cloud Specification | 10 | 7 | Architect, Lead Dev | 12800 | Yes
10 | 2.4 | API Integration Protocols (SIS, LMS, Payments) | 7 | 9 | Architect, Backend Dev | 8800 | Yes
11 | 2.5 | MILESTONE 2: Architecture & Specs Approved | 0 | 10 | Architect, PM | 0 | Yes
12 | 3.0 | DATA MIGRATION & SECURITY SETUP | 25 |  | DB Lead, Security Eng | 39500 | Yes
13 | 3.1 | Legacy Data Profiling & Cleansing | 10 | 11 | DB Lead, Data Analyst | 14000 | Yes
14 | 3.2 | Data Mapping & Automated ETL Scripts Dev | 10 | 13 | DB Lead, Backend Dev | 15200 | Yes
15 | 3.3 | Cloud Database Schema & Index Optimization | 5 | 14 | DB Lead | 6800 | Yes
16 | 3.4 | Data Encryption & RBAC Setup | 5 | 14 | Security Eng | 5500 | No
17 | 3.5 | MILESTONE 3: Migration Scripts & Security Ready | 0 | 15,16 | DB Lead, Security | 0 | Yes
18 | 4.0 | PORTAL CORE SYSTEM DEVELOPMENT | 35 |  | Dev Team (Full Stack) | 68000 | Yes
19 | 4.1 | Sprint 1: SSO & Unified Authentication | 10 | 17 | Lead Dev, Security | 17500 | Yes
20 | 4.2 | Sprint 2: Academic Records & Timetable Hub | 10 | 19 | Full Stack Devs (2) | 18200 | Yes
21 | 4.3 | Sprint 3: Course Enrolment & Cart Flow | 10 | 20 | Full Stack Devs (2) | 18500 | Yes
22 | 4.4 | Sprint 4: Financial Payment Gateway Integration | 8 | 21 | Lead Dev, FinTech Spec | 13800 | Yes
23 | 4.5 | Sprint 5: Mobile UI Optimization & Accessibility | 7 | 21 | Frontend Dev, UX Lead | 9800 | No
24 | 4.6 | MILESTONE 4: Core Development Feature Complete | 0 | 22,23 | Lead Dev, PM | 0 | Yes
25 | 5.0 | TESTING, QUALITY ASSURANCE & PILOT | 20 |  | QA Team, Security, Users | 34800 | Yes
26 | 5.1 | Functional, Performance & Load Testing | 8 | 24 | QA Lead, Tester | 11200 | Yes
27 | 5.2 | Independent Vulnerability & Penetration Testing | 5 | 26 | External Security Spec | 8500 | Yes
28 | 5.3 | User Acceptance Testing (UAT) with Students/Staff | 7 | 27 | QA Lead, BA, 50 Users | 9500 | Yes
29 | 5.4 | Defect Remediation & Stabilization | 5 | 28 | Dev Team, QA Lead | 5600 | Yes
30 | 5.5 | MILESTONE 5: UAT & Security Sign-Off | 0 | 29 | Sponsor, Registrar, PM | 0 | Yes
31 | 6.0 | TRAINING, DEPLOYMENT & CLOSURE | 15 |  | Change Lead, PM, Ops | 24200 | Yes
32 | 6.1 | End-User Guides & Video Walkthroughs | 5 | 30 | Change Lead, Technical Writer | 5400 | No
33 | 6.2 | Staff Training & Helpdesk Onboarding Clinics | 7 | 30 | Change Lead, Trainer | 7200 | No
34 | 6.3 | Production Cutover & Blue-Green Cloud Deployment | 4 | 30 | DevOps, Architect, DB Lead | 8200 | Yes
35 | 6.4 | Post-Implementation Review & Lessons Learned | 4 | 34 | PM, Sponsor, Team | 3400 | Yes
36 | 6.5 | MILESTONE 6: Final Project Closure & Decommissioning | 0 | 35 | Sponsor, PM | 0 | Yes

## Cost & Budget Plan
PROJECT BUDGET, LABOUR RATES & EXPENDITURE BREAKDOWN
Labour Rates, Capex, Opex, Contingency and Total Cost Baseline
1. HOURLY LABOUR RATES (8 hrs/day)
Resource Role | Team Member / Resource | Hourly Rate ($/hr) | Daily Rate ($/day) | Allocated Days | Subtotal Cost ($)
Project Manager | Tanvir Ahmed | 95 | 760 | 50 | 38000
Lead Solutions Architect | Contractor | 115 | 920 | 35 | 32200
Senior Full-Stack Developers (2) | Dev Team 1 & 2 | 85 | 680 | 80 | 54400
Database & Migration Specialist | Contractor / Momen A. | 95 | 760 | 45 | 34200
QA & Security Test Engineer | MD Rejvi Jaman M. | 80 | 640 | 40 | 25600
Change Management & Training Specialist | Change Lead | 75 | 600 | 30 | 18000
Business / Systems Analyst | Contractor | 85 | 680 | 30 | 20400
Total Direct Labour (Internal & Contracted)
2. NON-LABOUR & CAPITAL EXPENDITURE (CAPEX)
Expense Category | Vendor / Provider | Description | Cost Basis | Amount ($)
AWS Enterprise Cloud Hosting & Sandbox | Amazon Web Services | Multi-AZ Cloud Environment, RDS PostgreSQL, Redis | Fixed 6-mo Provision | 28500
SSO & Identity Licences (Okta / SAML) | Okta Enterprise | 1-Year University Identity Federation Tier | Annual Enterprise | 24000
Penetration Testing & Security Audit | CyberSec Assurance Ltd | Independent CREST-accredited penetration test | Fixed Quote | 16500
UI/UX Design & User Testing Lab | Figma & UsabilityHub | Design system tooling and remote student testing credits | Package | 6200
Training & Change Media Production | Media Studio | Video production for student/staff self-help guides | Production Quote | 9500
Payment Gateway Sandbox & Testing Escrow | Stripe / NAB Transact | API Integration, Webhook Testing & Compliance Escrow | Setup Fee | 5800
Total Non-Labour & Capex
3. COMPREHENSIVE BUDGET SUMMARY & CONTINGENCY ALLOCATION
Base Project Labour (Direct)
Base Capital & Non-Labour Costs
SUBTOTAL BASELINE COST (BAC)
Contingency Reserve (10% of BAC for Known-Unknown Technical Risks)
TOTAL COST BASELINE (BAC + Contingency)
Management Reserve (5% for Unforeseen Strategic Scope Changes)
TOTAL PROJECT BUDGET (Approved Project Ceiling)
APPROVED INSTITUTIONAL BUDGET CAP | 450000
BUDGET HEADROOM / BUFFER

## Risk Register & Heat Map
PROJECT OMNIPORTAL — RISK REGISTER & 5x5 ASSESSMENT
5x5 Scoring: Likelihood (1-5) x Impact (1-5) ¦ Extreme (15-25), High (10-14), Medium (5-9), Low (1-4)
Risk ID | Risk Description | Category | Likelihood (L) | Impact (I) | Score (L x I) | Priority | Owner | Strategy | Mitigation Action & Contingency Plan
R01 | Legacy Student Records Database schema mismatch and data corruption during automated ETL execution. | Technical | 4 | 5 |  | Extreme | Momen Ahmed | Mitigate | Perform dry-run ETL in sandbox with 10% sampling; build automated schema validation scripts with rollback checkpoints.
R02 | Cloud infrastructure latency or outage during Semester 1 peak enrolment traffic surge (>10k concurrent). | Operational | 3 | 5 |  | Extreme | Tanvir Ahmed | Mitigate | Configure AWS Auto-Scaling and Redis caching; conduct load/stress testing at 250% capacity (15k concurrent) prior to cutover.
R03 | Faculty and administrative staff resistance to adopting new unified marks entry and advising portal. | Organizational | 4 | 3 |  | High | MD Rejvi Jaman | Mitigate | Appoint 12 departmental 'Change Champions'; provide targeted 30-minute drop-in clinics and video micro-guides.
R04 | Data breach or student Personally Identifiable Information (PII) leak violating Australian Privacy Principles. | Compliance | 2 | 5 |  | High | Tanvir Ahmed | Mitigate | Implement AES-256 at-rest and TLS 1.3 in-transit encryption; conduct CREST-certified independent penetration testing.
R05 | Scope creep driven by conflicting customization demands across faculties (Business vs Health Science). | Scope | 4 | 3 |  | High | Tanvir Ahmed | Mitigate | Enforce strict Change Control Board (CCB) protocol; freeze non-critical functional enhancements for Phase 2 post-launch.
R06 | Resignation or illness of Lead Database & Migration Specialist during critical cutover window. | Resource | 2 | 4 |  | Medium | Momen Ahmed | Mitigate | Mandate comprehensive technical documentation in Confluence; cross-train Senior Backend Developer as secondary lead.
R07 | SSO authentication failure or latency spike connecting to on-premise Active Directory. | Technical | 3 | 3 |  | Medium | Tanvir Ahmed | Mitigate | Deploy cloud-replicated Azure AD / Okta connectors with fallback token cache to decouple from on-premise network latency.
R08 | Mobile UI rendering defects on legacy browser versions (older iOS/Android student handsets). | Technical | 3 | 2 |  | Medium | MD Rejvi Jaman | Mitigate | Use BrowserStack automated testing suite targeting 98% of student device demographic; set minimum OS support baseline.
R09 | Third-party payment gateway API rate limiting or timeout during tuition fee due dates. | External | 2 | 4 |  | Medium | Momen Ahmed | Mitigate | Establish asynchronous queueing (RabbitMQ) with exponential retry logic; negotiate enterprise burst rate with gateway vendor.
R10 | Tier-1 student helpdesk overwhelmed with password reset and multi-factor authentication (MFA) requests. | Operational | 4 | 2 |  | Medium | MD Rejvi Jaman | Mitigate | Implement automated self-service password reset (SSPR) workflow and deploy interactive FAQ chatbot on portal landing page.
5x5 RISK HEAT MAP MATRIX (Likelihood vs Impact)
Numbers in cells represent active project risks mapped to that severity coordinate.
Likelihood \ Impact | 1 - Insignificant | 2 - Minor | 3 - Moderate | 4 - Major | 5 - Severe
5 - Almost Certain | Low (5) | Medium (10) | High (15) | Extreme (20) | Extreme (25)
4 - Likely | Low (4) | Medium (8): R10 | High (12): R03, R05 | High (16) | Extreme (20): R01
3 - Possible | Low (3) | Medium (6): R08 | Medium (9): R07 | High (12) | Extreme (15): R02
2 - Unlikely | Low (2) | Low (4) | Medium (6) | Medium (8): R06, R09 | High (10): R04
1 - Rare | Low (1) | Low (2) | Low (3) | Medium (4) | Medium (5)

## Stakeholders & Communication
PROJECT OMNIPORTAL — STAKEHOLDER REGISTER & POWER-INTEREST ANALYSIS
Classification Grid: Manage Closely (H/H), Keep Satisfied (H/L), Keep Informed (L/H), Monitor (L/L)
Stakeholder ID | Stakeholder Group / Name | Internal / External | Power (Influence) | Interest | Power-Interest Quadrant | Core Expectations & Win Conditions | Potential Risks to Project | Engagement & Communication Strategy
SH01 | Chief Information Officer (CIO) / Project Sponsor | Internal | High | High | Manage Closely | Strategic digital alignment, delivery within $450k budget, zero security incidents. | Withholding project tranche funding if milestones breach SLAs. | Weekly 1-on-1 executive status briefing; immediate escalation of critical variances.
SH02 | University Registrar & Enrolment Operations | Internal | High | High | Manage Closely | Flawless student enrolment lifecycle, zero missing academic records, error-free timetabling. | Operational veto of cutover if data integrity cannot be verified. | Bi-weekly operational steering meetings, co-design of data validation criteria, sign-off on UAT.
SH03 | Academic Senate & Faculty Deans | Internal | High | Low | Keep Satisfied | No disruption to semester teaching; intuitive grade-submission interface. | Public academic pushback or boycotts if changes degrade workflow. | Monthly high-level progress digests; early faculty demo sessions during Faculty Board meetings.
SH04 | Student Representative Council (SRC) & Student Body | Internal | Low | High | Keep Informed | Modern, responsive mobile interface, fast course cart checkout, clear fee payment receipts. | Social media outcry and high resistance if platform is difficult to navigate. | Bi-weekly student email updates, beta testing focus groups (50 students), interactive FAQ video drops.
SH05 | Central IT Infrastructure & Cybersecurity Office | Internal | High | High | Manage Closely | 100% compliance with ISO 27001, seamless SSO integration, robust API security controls. | Security freeze on production deployment if pentest uncovers high vulnerabilities. | Joint weekly architectural reviews, security sign-off at each sprint boundary, audit log inspection.
SH06 | University Finance & Accounts Department | Internal | Medium | Low | Keep Satisfied | Automated reconciliation of tuition payments, compliance with PCI-DSS payment rules. | Reconciliation discrepancies delaying audit closure. | Monthly finance checkpoint, automated daily batch reconciliation reports during sandbox testing.
SH07 | Student Central Support & Helpdesk Staff | Internal | Low | High | Keep Informed | Reduced repetitive support calls, intuitive admin troubleshooting dashboard, clear knowledge base. | Staff panic and escalated wait times if training is inadequate. | Hands-on training clinics 3 weeks before launch; dedicated 'Hypercare' chat bridge during cutover.
SH08 | TEQSA & National Privacy Commissioner | External | High | Low | Keep Satisfied | Strict compliance with Higher Education Standards and Australian Privacy Principles. | Regulatory audits and penalties for data privacy infringements. | Maintain rigorous data protection impact assessments (DPIA) and audit trails for compliance verification.
PROJECT COMMUNICATION MATRIX
Stakeholder Group | Information Artefact | Objective / Purpose | Delivery Format / Channel | Frequency | Sender / Owner
Project Sponsor (CIO) | Executive Dashboard & Variance Report | Strategic oversight, EVM metrics (SPI/CPI), decision sign-offs | In-person briefing + PDF Summary | Weekly | Tanvir Ahmed (PM)
Steering Committee (Registrar, IT, Finance) | Project Steering Progress Pack | Review milestone achievements, approve change requests, clear blockers | Formal Committee Meeting & Minutes | Fortnightly | Tanvir Ahmed (PM)
Core Technical & Dev Team | Daily Stand-Up & Trello Sprint Board | Review daily task progress, identify blockers, sync dependencies | 15-minute Morning Stand-up (Teams) | Daily (Mon-Fri) | MD Rejvi Jaman (Delivery Lead)
Faculty & Academic Staff | Staff Transition Bulletin & Demo Videos | Demonstrate grade entry UI, outline cutover timeline, set training dates | Email Bulletin & Intranet Portal | Monthly | Momen Ahmed (Governance Lead)
Student Body & SRC | OmniPortal Launch Updates & FAQs | Inform on feature benefits, mobile access, credentials migration | Student News Hub, App notification, Instagram | Bi-weekly / Milestone | MD Rejvi Jaman (Change Lead)
Helpdesk & Operations Team | Technical Runbook & Hypercare Protocols | Equip tier-1 support with triage workflows and common resolutions | Interactive Workshop & Confluence Docs | Sprint 5 & Launch Week | Tanvir Ahmed & MD Rejvi Jaman

## Quality, Change & RACI
PROJECT OMNIPORTAL — QUALITY METRICS, CHANGE CONTROL & RACI
Section 4 Deliverables: Measurable Quality Thresholds, Approved Scope Change, and RACI Matrix
1. QUALITY REQUIREMENTS & VERIFICATION METRICS
Quality Area | Target Metric / Indicator | Acceptance Threshold | Measurement Method | Frequency | Control Action if Failed
System Availability | Operational Uptime | >= 99.95% during semester terms | AWS CloudWatch Synthetics / Pingdom | Continuous (24/7) | Failover to hot-standby AWS replica; page DevOps on-call immediately.
Performance & Load | Page Load Time at Peak Concurrent Users | < 1.8s load time at 12,000 concurrent sessions | JMeter automated load testing script | End of Sprint 4 & 5 | Optimize database query indices; configure Redis caching for static timetable assets.
Data Migration Integrity | Student Academic Records Fidelity | 100.0% accurate field match (zero data loss) | Automated checksum hash comparison against legacy SIS | At each ETL test run | Halt cutover, execute script rollback, analyze schema mismatch log.
Software Defect Density | Open Defect Count at UAT Exit | Zero Severity-1 (Critical) or Severity-2 (High) defects | Jira / Trello bug tracker triage | Weekly bug scrub | Mandate code-freeze sprint dedicated strictly to defect remediation.
Student Usability | System Usability Scale (SUS) Score | >= 80/100 across 50 pilot student evaluators | Standard SUS 10-question post-pilot survey | Sprint 5 UAT | Execute 3-day UX wireframe refinement focusing on low-scoring workflows.
Cybersecurity & Privacy | Vulnerability Severity Rating | Zero High/Critical CVEs; OWASP Top 10 compliance | Independent CREST-certified penetration test | Pre-Deployment (Wk 20) | Remediate code vulnerabilities within 72 hours; rerun automated security scan.
2. FORMAL CHANGE MANAGEMENT LOG — CHANGE REQUEST CR-01
Change Request ID | CR-01
Change Title | Mandatory Multi-Factor Authentication (MFA) & Mobile Push SSO Integration
Date Submitted / Originator | 14-Apr-2026 ¦ University Cybersecurity Advisory Board
Reason for Change | New Australian Cyber Security Centre (ACSC) Essential Eight directives requiring mandatory MFA for all tertiary education portals containing sensitive student financial and personal records.
Scope Impact | Add Twilio SMS verification microservice, Authenticator app TOTP hooks, and 'Remember Device for 30 Days' secure cookie logic.
Schedule Impact | +8 Working Days to Sprint 1 authentication track. Absorbed by fast-tracking UI testing in parallel with Sprint 2 development (Zero net change to 17-Jul-2026 Go-Live date).
Cost Impact | +$14,500 AUD (Twilio SMS setup, security developer sprint effort). Funded entirely from the $38,500 Contingency Reserve. Baseline budget remains unaffected.
Risk Impact | Drastically reduces risk R04 (Data Breach) from High to Low. Introduces minor user friction risk (R10), mitigated by self-service onboarding wizard.
CCB Evaluation & Decision | APPROVED by Project Sponsor (CIO) and Steering Committee on 18-Apr-2026. Incorporated into Sprint 3 development baseline.
3. RACI RESPONSIBILITY ASSIGNMENT MATRIX
R = Responsible (Completes work) ¦ A = Accountable (Final decision) ¦ C = Consulted (Provides input) ¦ I = Informed (Kept updated)
WBS Phase / Activity | Sponsor (CIO) | Project Manager | Solutions Architect | Lead Dev Team | DB Migration Lead | QA & Security Lead | Change & Training Lead
1.0 Project Initiation & Charter Sign-off | A | R | C | I | I | I | C
2.0 Requirements & Architectural Blueprint | I | A | R | C | C | C | C
3.0 Data Migration, Cleansing & DB Setup | I | A | C | C | R | C | I
4.0 Core Portal Development & Sprint Delivery | I | A | C | R | C | C | I
5.0 Testing, Security Audit & UAT | I | A | C | C | C | R | C
6.0 Change Training, Cutover & Project Closure | A | R | C | C | C | C | R

## Tracking & EVM Dashboard
PROJECT OMNIPORTAL — STATUS & EARNED VALUE MANAGEMENT (EVM) DASHBOARD
Mid-Project Progress Review at Week 14 (Data Date: 08 May 2026)
PLANNED VALUE (PV) | EARNED VALUE (EV) | ACTUAL COST (AC) | SCHEDULE VAR (SV) | COST VAR (CV) | SPI (EV / PV) | CPI (EV / AC)
225000 | 198000 | 210000
EVM FORECASTING & VARIANCE ANALYSIS
Budget at Completion (BAC) | 385000 | Approved Base Cost Baseline excluding management reserve
Estimate at Completion (EAC) |  | EAC = BAC / CPI (Predicts total cost if current spending efficiency continues: $408,271)
Variance at Completion (VAC) |  | VAC = BAC - EAC (-$23,271 projected overrun if uncorrected; fully covered by $38.5k contingency)
To-Complete Performance Index (TCPI) |  | Cost efficiency required on remaining work to achieve original BAC: 1.068
Schedule Status | 10 Days Behind Plan (SPI = 0.880) | Critical path activity 3.2 (Automated ETL Scripts) encountered legacy schema errors.
Cost Status | $12,000 Unfavourable Variance (CPI = 0.943) | Additional senior database engineering hours required to resolve foreign-key schema conflicts.
CRITICAL VARIANCE & CORRECTIVE MANAGEMENT ACTION REPORT
Identified Variance | At Week 14, cumulative earned progress is 51.4% against a planned baseline of 58.4% (SPI = 0.880, Schedule Variance = -$27,000; 10 business days delayed on Critical Path task 3.2). Cost variance is -$12,000 (CPI = 0.943).
Root Cause Analysis | Legacy Ellucian Banner database contained 14 unindexed tables and inconsistent student address data models that caused automated ETL transformation scripts to crash repeatedly during test runs, requiring unexpected schema normalization.
Management Decision & Corrective Action | 1. Fast-Tracking / Crashing: Allocated $6,800 from the Contingency Reserve to onboard an external Senior ETL Data Engineer for 10 days to run data cleansing in parallel with API stub creation. 2. Work Sequence Adjustment: Re-sequenced Sprint 3 (Course Enrolment) front-end mockups to begin immediately using simulated mock data rather than waiting for 100% database population. 3. Outcome: Recovered 7 of the 10 lost days by Week 16; SPI rebounded to 0.96; final go-live milestone remains protected.

## Issues, Closure & Lessons
PROJECT OMNIPORTAL — ISSUE LOG, CLOSURE CHECKLIST & BENEFITS REALISATION
Operational Issue Tracking, Handover Verification and Long-term Realisation Targets
1. PROJECT ISSUE LOG & RESOLUTIONS
Issue ID | Issue Description | Severity | Date Raised | Owner | Corrective Action Taken | Resolution Date | Status
ISS-01 | Legacy Banner database lacked composite foreign key indices, creating 14-hour ETL batch execution times. | High | 12-Apr-2026 | Momen Ahmed | Created temporary staging indices and partitioned student record batches by cohort year. ETL time reduced to 42 minutes. | 22-Apr-2026 | Closed
ISS-02 | UAT pilot users reported confusion regarding multi-step course cart checkout and fee breakdown. | Medium | 02-May-2026 | MD Rejvi Jaman | Conducted rapid 3-day UX wireframe redesign; implemented a streamlined 2-step checkout wizard with clear fee summaries. | 10-May-2026 | Closed
ISS-03 | Stripe payment gateway sandbox webhook timeouts during bulk payment simulations. | Medium | 14-May-2026 | Tanvir Ahmed | Configured asynchronous Redis message queue with exponential backoff and automatic retry handler. | 21-May-2026 | Closed
2. PROJECT CLOSURE & OPERATIONAL HANDOVER CHECKLIST
Checklist Item | Category | Verification Criteria | Responsible Party | Sign-Off Status
All 28 WBS deliverables completed and verified against scope criteria | Deliverables | 100% acceptance certificates signed by Registrar & CIO | Tanvir Ahmed (PM) | Approved
Legacy portal data successfully extracted, verified and decommissioned | Data & Infrastructure | Zero data loss audit confirmed; old servers archived | Momen Ahmed (DB Lead) | Approved
Final independent penetration test and security audit cleared | Governance & Privacy | Zero critical/high vulnerabilities; ISO 27001 certificate | Security Lead | Approved
Operational Runbook and tier-1/tier-2 support triage guides published | Operations | Full documentation uploaded to IT Service Desk Confluence | MD Rejvi Jaman | Approved
End-user training completed (94% staff completion; student video live) | Change Management | Training LMS logs verified; student feedback >= 85% | Change Lead | Approved
Financial accounts closed, supplier contracts reconciled and audited | Financial | Final cost audit confirmed within approved $450k envelope | Momen Ahmed & Finance | Approved
3. POST-LAUNCH BENEFITS REALISATION SCHEDULE
Strategic Benefit | Baseline Metric (Pre-Project) | Target Metric (Post-Project) | Evaluation Timeline | Benefit Owner
Reduction in Student Enrolment Helpdesk Enquiries | 4,200 enquiries / semester | < 2,100 enquiries (50% reduction) | 3 Months Post-Launch | University Registrar
Annual Software Licensing & Maintenance Cost Savings | $185,000 / year across 4 systems | < $65,000 / year (Net saving: $120,000/yr) | 12 Months Post-Launch | Chief Information Officer
Student Portal Usability & Satisfaction Rating | 48% satisfaction on legacy portal | >= 85% positive rating on Student Survey | 6 Months Post-Launch | Student Central Director
Course Enrolment Processing Speed | Average 14.5 minutes per student | < 3.5 minutes per student | 1 Month Post-Launch | Enrolment Operations Lead